## History
Pre-test Report History
Date | Revision | Modification
2025-01-14 | 1.0 | 1.Initial version. 2.Based on the Meta_Clemente_Development_Schedule_v9_1230 to plan BIOS release and implemention schedule
2025-02-08 | 1.1 | Update Release plan
2025-02-21 | 1.2 | 1. Adjust release date for pull in the RAS feature & PXE boot
2025-03-21 | 1.3 | 1. Base on the schedule 10.1_0310 to Adjust the release schedule 2. change the version naming to meet Meta naming format
2025-04-07 | 1.4 | 1. Adjust release schedule 2. Add DVT release plan.

## BIOS Release PlanV1.4
| EVT2 Bring-up |  | 2025-02-25
| L10 Compute tray Shipment date |  | 2025-03-17
| SIT EVT test start |  | 2025-04-08
| EVT exit Date |  | 2025-06-12
| DVT exit Date |  | 2025-10-28
Phase | Release Date | Version | Function |  | Comment | Remark
EVT | 2025-02-21 | P21MT01X | Bring-up BIOS initial |  | This version only use for EVT2 Bring-up.
|  |  | BIOS upgrade/downgrade |  | BIOS requirement Section 2.3.2
|  |  | Compute tray design porting | - PCIe Bifurcation
|  |  |  | - GPIO configuration |  | SIT-2/14: Please refer the provide the GPIO table BIOS-2/19 : Confirmed with NV, NV does not provide the document for the GPIO definition because NV does not allow us to perform any individual GPIO control or monitoring.
- HW design configuraiton
|  |  | Serial console | - consosle Redirection
- Serial over lan
- Output POST code to BMC SOL
|  |  | Network stack | Initial implement
|  |  |  | PXE boot(IPV6 & IPV4) | BIOS Reqirement Section 2.2.11 | BIOS-2/21 Move up for meet SIT testing requirement.
| 2025-03-21 | CLE101 | Transfer Bring-up to Official release | - Integrated soulitions that fix Bring-up issue |  | BIOS-2/21 The release date is contingent upon the bring-up completion date.
| 2025-04-07 | CLE102 | IPMI 2.0 | - SSIF initialization | Grace is use SSIF for IPMI command
|  |  | System boot | - Boot from HDD/USB device. | BIOS Requirement Section 2.3.1
- efibootmgr
|  |  | RAS Feature | NV RAS components |  | SIT-2/14: What's the implment status for NVRAStool? BIOS-2/19: Based on the RAS tool user guide, BIOS needs to enable APEI for error injection, and APEI is enabled by default. RAStools also include BMC requirements. After discussing with BMC-Mark, the current BMC should be able to support it. We can discuss with BMC further if got any problem during testing. BIOS-2/21: Move up based on SIT test schedule
|  |  | System components information | Initial implement
|  |  | BIOS setup menu | Initial implement
|  |  | ACPI tables | Initial implement
|  |  | SMBIOS structures | Initial implement
Issue fixes
| 2025-04-16 | CLE103 | ACPI implement check |  | BIOS Requirement Section 2.4
|  |  | SMBIOS implement check |  | BIOS Requirement Section 2.4
|  |  | RAS features behavior and implement check | - Error inject for CPU/PCIE/Memory | - BIOS Requirement section 3 - Following NV Grance RAS feture requirement | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: I will adjust and update the schedule for the RAS features. BIOS-2/21: Move up for meet SIT test requirement
|  |  |  | - Error handling for CPU/PCIe/Memory |  | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: I will adjust and update the schedule for the RAS features. BIOS-2/21: Move up for meet SIT test requirement
|  |  |  | - Error reporting |  | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: I will adjust and update the schedule for the RAS features. BIOS-2/21: Move up for meet SIT test requirement
|  |  |  | - DPC event loging | BIOS requirement Section 4.4.2
|  |  | System Components information implement check | - CPU/Memory/PCIe | BIOS requriement section 2.2
|  |  |  | - Component information, Display SKU and HW revision in setup menu | BIOS requriement section 2.2.18
Issue fixes
| 2025-04-23 | CLE104 | Network Stack | - HTTP boot | BIOS requirement Sectgion 2.2.11 . Including Two OEM IPMI command, NetFN: 0x30, CMD: 0x57/0x58
|  |  | BMC & IPMI advanced requirements | - Wait for BMC IPMI command ready | BIOS requirement Section 2.2.15
|  |  | System Management | - POST code, following silicon vendor's Implementation | BIOS requirement Section 2.5
|  |  | System power setting check for match spec define |  | BIOS Requirement section 2.8
Issue fixes
| 2025-04-30 | CLE105 | System Components | TPM | BIOS Requirement Section 2.2.9
|  |  | PCIe Managed Power Control(Hotplug) |  | BIOS requirement Section 4.4.3
|  |  | IPMI CMOS Clear |  | BIOS Requirement Section 2.3.3
|  |  | FRB2 Watchdog |  | BIOS Requirement Section 2.3.4
|  |  | SMBIOS dynamic update | - Update SMBIOS by read FRU.
|  |  | BIOS setup menu advanced | - Don't show the system information in POST Screen | BIOS requriement section 2.1
|  |  |  | - Add 7 sec waiting time for user input to enter BIOS setup. | BIOS requriement section 2.1
Issue fixes
| 2025-05-07 | CLE106 | Sytstem Security | UEFI secure boot | BIOS Requirement 2.6
|  |  | OEM SEL Implement | - PCIe error SEL | BIOS Requirement section 5 * UPI Error/IIO Error/UPI/Boot Guard/MCA Error are Intel Platform feture, Not supported in the GB200/GB300 Platform | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: In Nvidia Grace architecture, NV RAS FW notifies BMC about RAS event by using PLDM over MCTP messages. CPU/Memory/PCIe errors are reported to BMC with CPER format, BMC is responsible for RAS error logging, BIOS only reported POST errors.
- Memory error SEL
- POST Error Event SEL
- PCIe device failure events SEL
- Memory device failure events SEL
|  |  | System management | - update PPIN to SMBIOS type 11 | BIOS Requirement Section 2.5
|  |  |  | - Communicate to BMC by Send PPIN and GET PPIN | BIOS requirement Section 2.5
|  |  | POST code for error DIMM lication and error code |  |  | BIOS-2/21 For NVIDIA Grace architecture, memory training is done by NV BootFW, there is no chance for BIOS to do this feature due to BIOS does not take over yet.
|  |  | BMC & IPMI relate implement | - Send BIOS version to BMC | BIOS requirement Section 2.2.15 NetFN: 0x06, CMD:0x58
|  |  |  | - Send PCIe Configuraton to BMC | BIOS requirement Section 2.2.15 NetFN:0x30 CMD: 0x71 (OEM command)
|  |  |  | - Send Boot order to BMC | BIOS requirement Section 2.2.15 NetFN:0x30 CMD: 0x52 (OEM command)
|  |  |  | - able to set and get BIOS boot order throuth BMC | BIOS Requirement Section 2.3.1.1 NetFN: 0x30 CMD_OEM_SET_BOOT_ORDER 0x52 CMD_OEM_GET_BOOT_ORDER 0x53
Issue fixes
| 2025-05-14 | CLE107 | System Performance tuning |  | BIOS Requirement Section 2.7
|  |  | Boot order arrange | - Respect omission of DHCPv4 / DHCPv6 if requested | BIOS Requirement Section 2.3.1.1
|  |  |  | - Not waiting for BMC, BIOS shall clear [boot flags valid(bit7)] when get the command back | BIOS Requirement Section 2.3.1.1
|  |  |  | - Disabe unuse PXE boot device, only keep the IPV6/IPV4 UEFI on CX7 at CPU0 | Request in visit meeting @ 1/8
|  |  | Boot Time |  | BIOS Requirement Section 2.3.1.2
Issue fixes
| 2025-05-21 | CLE108 | Manufacturing requirement |  | BIOS Requirement 2.9
Issue fixes
| 2025-05-28 | CLE109 | Issue fixes
| 2025-06-04 | CLE110 | Issue fixes
DVT | 2025-06-18 | CLE201 | Issue Fixes
|  |  | RC code update |  |  | Base on NV RC/AMI code base release date.
|  |  | Customer Extend Features |  |  | Depend on meta whter have the additional' requirment.
| 2025-07-02 | CLE202 | Issue Fixes
|  |  | RC code update |  |  | Base on NV RC/AMI code base release date.
|  |  | Customer Extend Features |  |  | Depend on meta whter have the additional' requirment.
| 2025-07-16 | CLE203 | Issue Fixes
|  |  | RC code update |  |  | Base on NV RC/AMI code base release date.
|  |  | Customer Extend Features |  |  | Depend on meta whter have the additional' requirment.
| 2025-07-30 | CLE204 | Issue Fixes
|  |  | RC code update |  |  | Base on NV RC/AMI code base release date.
|  |  | Customer Extend Features |  |  | Depend on meta whter have the additional' requirment.
| 2025-08-13 | CLE205 | Issue Fixes
|  |  | RC code update |  |  | Base on NV RC/AMI code base release date.
|  |  | Customer Extend Features |  |  | Depend on meta whter have the additional' requirment.
| 2025-08-27 | CLE206 | Issue Fixes
|  |  | RC code update |  |  | Base on NV RC/AMI code base release date.
|  |  | Customer Extend Features |  |  | Depend on meta whter have the additional' requirment.
| 2025-09-10 | CLE207 | Issue Fixes
|  |  | RC code update |  |  | Base on NV RC/AMI code base release date.
|  |  | Customer Extend Features |  |  | Depend on meta whter have the additional' requirment.
| 2025-09-24 | CLE208 | Issue Fixes
|  |  | RC code update |  |  | Base on NV RC/AMI code base release date.
|  |  | Customer Extend Features |  |  | Depend on meta whter have the additional' requirment.
| 2025-10-08 | CLE209 | Issue Fixes
|  |  | RC code update |  |  | Base on NV RC/AMI code base release date.
|  |  | Customer Extend Features |  |  | Depend on meta whter have the additional' requirment.
| 2025-10-22 | CLE210 | Issue Fixes
|  |  | RC code update |  |  | Base on NV RC/AMI code base release date.
|  |  | Customer Extend Features |  |  | Depend on meta whter have the additional' requirment.

## BIOS Release PlanV1.3
EVT2 Bring-up |  | 2025-02-25
L10 Compute tray Shipment date |  | 2025-03-17
SIT EVT test start |  | 2025-04-08
EVT exit Date |  | 2025-06-12
Release Date | Version | Function |  | Comment | Remark
2025-02-21 | P21MT01X | Bring-up BIOS initial |  | This version only use for EVT2 Bring-up.
|  | BIOS upgrade/downgrade |  | BIOS requirement Section 2.3.2
|  | Compute tray design porting | - PCIe Bifurcation
|  |  | - GPIO configuration |  | SIT-2/14: Please refer the provide the GPIO table BIOS-2/19 : Confirmed with NV, NV does not provide the document for the GPIO definition because NV does not allow us to perform any individual GPIO control or monitoring.
- HW design configuraiton
|  | Serial console | - consosle Redirection
- Serial over lan
- Output POST code to BMC SOL
|  | Network stack | Initial implement
|  |  | PXE boot(IPV6 & IPV4) | BIOS Reqirement Section 2.2.11 | BIOS-2/21 Move up for meet SIT testing requirement.
2025-03-21 | CLE101 | Transfer Bring-up to Official release | - Integrated soulitions that fix Bring-up issue |  | BIOS-2/21 The release date is contingent upon the bring-up completion date.
2025-04-02 | CLE102 | IPMI 2.0 | - SSIF initialization | Grace is use SSIF for IPMI command
|  | System boot | - Boot from HDD/USB device. | BIOS Requirement Section 2.3.1
- efibootmgr
|  | RAS Feature | NV RAS components |  | SIT-2/14: What's the implment status for NVRAStool? BIOS-2/19: Based on the RAS tool user guide, BIOS needs to enable APEI for error injection, and APEI is enabled by default. RAStools also include BMC requirements. After discussing with BMC-Mark, the current BMC should be able to support it. We can discuss with BMC further if got any problem during testing. BIOS-2/21: Move up based on SIT test schedule
|  | System components information | Initial implement
|  | BIOS setup menu | Initial implement
|  | ACPI tables | Initial implement
|  | SMBIOS structures | Initial implement
Issue fixes
2025-04-09 | CLE103 | ACPI implement check |  | BIOS Requirement Section 2.4
|  | SMBIOS implement check |  | BIOS Requirement Section 2.4
|  | RAS features behavior and implement check | - Error inject for CPU/PCIE/Memory | - BIOS Requirement section 3 - Following NV Grance RAS feture requirement | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: I will adjust and update the schedule for the RAS features. BIOS-2/21: Move up for meet SIT test requirement
|  |  | - Error handling for CPU/PCIe/Memory |  | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: I will adjust and update the schedule for the RAS features. BIOS-2/21: Move up for meet SIT test requirement
|  |  | - Error reporting |  | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: I will adjust and update the schedule for the RAS features. BIOS-2/21: Move up for meet SIT test requirement
|  |  | - DPC event loging | BIOS requirement Section 4.4.2
|  | System Components information implement check | - CPU/Memory/PCIe | BIOS requriement section 2.2
|  |  | - Component information, Display SKU and HW revision in setup menu | BIOS requriement section 2.2.18
Issue fixes
2025-04-16 | CLE104 | Network Stack | - HTTP boot | BIOS requirement Sectgion 2.2.11 . Including Two OEM IPMI command, NetFN: 0x30, CMD: 0x57/0x58
|  | BMC & IPMI advanced requirements | - Wait for BMC IPMI command ready | BIOS requirement Section 2.2.15
|  | System Management | - POST code, following silicon vendor's Implementation | BIOS requirement Section 2.5
|  | System power setting check for match spec define |  | BIOS Requirement section 2.8
Issue fixes
2025-04-23 | CLE105 | System Components | TPM | BIOS Requirement Section 2.2.9
|  | PCIe Managed Power Control(Hotplug) |  | BIOS requirement Section 4.4.3
|  | IPMI CMOS Clear |  | BIOS Requirement Section 2.3.3
|  | FRB2 Watchdog |  | BIOS Requirement Section 2.3.4
|  | SMBIOS dynamic update | - Update SMBIOS by read FRU.
|  | BIOS setup menu advanced | - Don't show the system information in POST Screen | BIOS requriement section 2.1
|  |  | - Add 7 sec waiting time for user input to enter BIOS setup. | BIOS requriement section 2.1
Issue fixes
2025-04-30 | CLE106 | Sytstem Security | UEFI secure boot | BIOS Requirement 2.6
|  | OEM SEL Implement | - PCIe error SEL | BIOS Requirement section 5 * UPI Error/IIO Error/UPI/Boot Guard/MCA Error are Intel Platform feture, Not supported in the GB200/GB300 Platform | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: In Nvidia Grace architecture, NV RAS FW notifies BMC about RAS event by using PLDM over MCTP messages. CPU/Memory/PCIe errors are reported to BMC with CPER format, BMC is responsible for RAS error logging, BIOS only reported POST errors.
- Memory error SEL
- POST Error Event SEL
- PCIe device failure events SEL
- Memory device failure events SEL
|  | System management | - update PPIN to SMBIOS type 11 | BIOS Requirement Section 2.5
|  |  | - Communicate to BMC by Send PPIN and GET PPIN | BIOS requirement Section 2.5
|  | POST code for error DIMM lication and error code |  |  | BIOS-2/21 For NVIDIA Grace architecture, memory training is done by NV BootFW, there is no chance for BIOS to do this feature due to BIOS does not take over yet.
|  | BMC & IPMI relate implement | - Send BIOS version to BMC | BIOS requirement Section 2.2.15 NetFN: 0x06, CMD:0x58
|  |  | - Send PCIe Configuraton to BMC | BIOS requirement Section 2.2.15 NetFN:0x30 CMD: 0x71 (OEM command)
|  |  | - Send Boot order to BMC | BIOS requirement Section 2.2.15 NetFN:0x30 CMD: 0x52 (OEM command)
|  |  | - able to set and get BIOS boot order throuth BMC | BIOS Requirement Section 2.3.1.1 NetFN: 0x30 CMD_OEM_SET_BOOT_ORDER 0x52 CMD_OEM_GET_BOOT_ORDER 0x53
Issue fixes
2025-05-07 | CLE107 | System Performance tuning |  | BIOS Requirement Section 2.7
|  | Boot order arrange | - Respect omission of DHCPv4 / DHCPv6 if requested | BIOS Requirement Section 2.3.1.1
|  |  | - Not waiting for BMC, BIOS shall clear [boot flags valid(bit7)] when get the command back | BIOS Requirement Section 2.3.1.1
|  |  | - Disabe unuse PXE boot device, only keep the IPV6/IPV4 UEFI on CX7 at CPU0 | Request in visit meeting @ 1/8
|  | Boot Time |  | BIOS Requirement Section 2.3.1.2
Issue fixes
2025-05-14 | CLE108 | Manufacturing requirement |  | BIOS Requirement 2.9
Issue fixes
2025-05-21 | CLE109 | Issue fixes
2025-05-28 | CLE110 | Issue fixes

## BIOS Release PlanV1.2
EVT2 Bring-up |  | 2025-02-25
L10 Compute tray Shipment date |  | 2025-03-03
SIT EVT test start |  | 2025-03-11
EVT exit Date |  | 2025-05-13
Release Date | Version | Function |  | Comment | Remark
2025-02-21 | P21MT01X | Bring-up BIOS initial |  | This version only use for EVT2 Bring-up.
|  | BIOS upgrade/downgrade |  | BIOS requirement Section 2.3.2
|  | Compute tray design porting | - PCIe Bifurcation
|  |  | - GPIO configuration |  | SIT-2/14: Please refer the provide the GPIO table BIOS-2/19 : Confirmed with NV, NV does not provide the document for the GPIO definition because NV does not allow us to perform any individual GPIO control or monitoring.
- HW design configuraiton
|  | Serial console | - consosle Redirection
- Serial over lan
- Output POST code to BMC SOL
|  | Network stack | Initial implement
|  |  | PXE boot(IPV6 & IPV4) | BIOS Reqirement Section 2.2.11 | BIOS-2/21 Move up for meet SIT testing requirement.
2025-03-05 | P21MT01A | Transfer Bring-up to Official release | - Integrated soulitions that fix Bring-up issue |  | BIOS-2/21 The release date is contingent upon the bring-up completion date.
2025-03-14 | P21MT02A | IPMI 2.0 | - SSIF initialization | Grace is use SSIF for IPMI command
|  | System boot | - Boot from HDD/USB device. | BIOS Requirement Section 2.3.1
- efibootmgr
|  | RAS Feature | NV RAS components |  | SIT-2/14: What's the implment status for NVRAStool? BIOS-2/19: Based on the RAS tool user guide, BIOS needs to enable APEI for error injection, and APEI is enabled by default. RAStools also include BMC requirements. After discussing with BMC-Mark, the current BMC should be able to support it. We can discuss with BMC further if got any problem during testing. BIOS-2/21: Move up based on SIT test schedule
|  | System components information | Initial implement
|  | BIOS setup menu | Initial implement
|  | ACPI tables | Initial implement
|  | SMBIOS structures | Initial implement
Issue fixes
2025-03-21 | P21MT03A | ACPI implement check |  | BIOS Requirement Section 2.4
|  | SMBIOS implement check |  | BIOS Requirement Section 2.4
|  | RAS features behavior and implement check | - Error inject for CPU/PCIE/Memory | - BIOS Requirement section 3 - Following NV Grance RAS feture requirement | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: I will adjust and update the schedule for the RAS features. BIOS-2/21: Move up for meet SIT test requirement
|  |  | - Error handling for CPU/PCIe/Memory |  | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: I will adjust and update the schedule for the RAS features. BIOS-2/21: Move up for meet SIT test requirement
|  |  | - Error reporting |  | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: I will adjust and update the schedule for the RAS features. BIOS-2/21: Move up for meet SIT test requirement
|  |  | - DPC event loging | BIOS requirement Section 4.4.2
|  | System Components information implement check | - CPU/Memory/PCIe | BIOS requriement section 2.2
|  |  | - Component information, Display SKU and HW revision in setup menu | BIOS requriement section 2.2.18
Issue fixes
2025-03-28 | P21MT04A | Network Stack | - HTTP boot | BIOS requirement Sectgion 2.2.11 . Including Two OEM IPMI command, NetFN: 0x30, CMD: 0x57/0x58
|  | BMC & IPMI advanced requirements | - Wait for BMC IPMI command ready | BIOS requirement Section 2.2.15
|  | System Management | - POST code, following silicon vendor's Implementation | BIOS requirement Section 2.5
|  | System power setting check for match spec define |  | BIOS Requirement section 2.8
Issue fixes
2025-04-04 | No Rlease |  |  | 4/3~4/4 Taiwan Holiday
2025-04-11 | P21MT05A | System Components | TPM | BIOS Requirement Section 2.2.9
|  | PCIe Managed Power Control(Hotplug) |  | BIOS requirement Section 4.4.3
|  | IPMI CMOS Clear |  | BIOS Requirement Section 2.3.3
|  | FRB2 Watchdog |  | BIOS Requirement Section 2.3.4
|  | SMBIOS dynamic update | - Update SMBIOS by read FRU.
|  | BIOS setup menu advanced | - Don't show the system information in POST Screen | BIOS requriement section 2.1
|  |  | - Add 7 sec waiting time for user input to enter BIOS setup. | BIOS requriement section 2.1
Issue fixes
2025-04-18 | P21MT06A | Sytstem Security | UEFI secure boot | BIOS Requirement 2.6
|  | OEM SEL Implement | - PCIe error SEL | BIOS Requirement section 5 * UPI Error/IIO Error/UPI/Boot Guard/MCA Error are Intel Platform feture, Not supported in the GB200/GB300 Platform | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: In Nvidia Grace architecture, NV RAS FW notifies BMC about RAS event by using PLDM over MCTP messages. CPU/Memory/PCIe errors are reported to BMC with CPER format, BMC is responsible for RAS error logging, BIOS only reported POST errors.
- Memory error SEL
- POST Error Event SEL
- PCIe device failure events SEL
- Memory device failure events SEL
|  | System management | - update PPIN to SMBIOS type 11 | BIOS Requirement Section 2.5
|  |  | - Communicate to BMC by Send PPIN and GET PPIN | BIOS requirement Section 2.5
|  | POST code for error DIMM lication and error code |  |  | BIOS-2/21 For NVIDIA Grace architecture, memory training is done by NV BootFW, there is no chance for BIOS to do this feature due to BIOS does not take over yet.
|  | BMC & IPMI relate implement | - Send BIOS version to BMC | BIOS requirement Section 2.2.15 NetFN: 0x06, CMD:0x58
|  |  | - Send PCIe Configuraton to BMC | BIOS requirement Section 2.2.15 NetFN:0x30 CMD: 0x71 (OEM command)
|  |  | - Send Boot order to BMC | BIOS requirement Section 2.2.15 NetFN:0x30 CMD: 0x52 (OEM command)
|  |  | - able to set and get BIOS boot order throuth BMC | BIOS Requirement Section 2.3.1.1 NetFN: 0x30 CMD_OEM_SET_BOOT_ORDER 0x52 CMD_OEM_GET_BOOT_ORDER 0x53
Issue fixes
2025-04-25 | P21MT07A | System Performance tuning |  | BIOS Requirement Section 2.7
|  | Boot order arrange | - Respect omission of DHCPv4 / DHCPv6 if requested | BIOS Requirement Section 2.3.1.1
|  |  | - Not waiting for BMC, BIOS shall clear [boot flags valid(bit7)] when get the command back | BIOS Requirement Section 2.3.1.1
|  |  | - Disabe unuse PXE boot device, only keep the IPV6/IPV4 UEFI on CX7 at CPU0 | Request in visit meeting @ 1/8
|  | Boot Time |  | BIOS Requirement Section 2.3.1.2
Issue fixes
2025-05-02 | P21MT08A | Manufacturing requirement |  | BIOS Requirement 2.9
Issue fixes
2025-05-09 | P21MT09A | Issue fixes

## BIOS Release PlanV1.1
L10 Compute tray Shipment date |  | 2025-02-26
EVT exit Date |  | 2025-05-13
Release Date | Version | Function |  | Comment | Remark
2025-02-14 | P21MT01X | Bring-up BIOS initial |  | This version only use for EVT2 Bring-up.
|  | BIOS upgrade/downgrade |  | BIOS requirement Section 2.3.2
|  | Compute tray design porting | - PCIe Bifurcation
|  |  | - GPIO configuration |  | SIT-2/14: Please refer the provide the GPIO table BIOS-2/19 : Confirmed with NV, NV does not provide the document for the GPIO definition because NV does not allow us to perform any individual GPIO control or monitoring.
- HW design configuraiton
|  | Serial console | - consosle Redirection
- Serial over lan
- Output POST code to BMC SOL
2025-02-26 | P21MT01A | Transfer Bring-up to Official release | - Integrated soulitions that fix Bring-up issue
2025-03-07 | P21MT02A | IPMI 2.0 | - SSIF initialization | Grace is use SSIF for IPMI command
|  | System boot | - Boot from HDD/USB device. | BIOS Requirement Section 2.3.1
- efibootmgr
|  | System components information | Initial implement
|  | BIOS setup menu | Initial implement
|  | ACPI tables | Initial implement
|  | SMBIOS structures | Initial implement
|  | Network stack | Initial implement
2025-03-14 | P21MT03A | ACPI implement check |  | BIOS Requirement Section 2.4
|  | SMBIOS implement check |  | BIOS Requirement Section 2.4
|  | System Components information implement check | - CPU/Memory/PCIe | BIOS requriement section 2.2
|  |  | - Component information, Display SKU and HW revision in setup menu | BIOS requriement section 2.2.18
|  | BIOS setup menu advanced | - Don't show the system information in POST Screen | BIOS requriement section 2.1
|  |  | - Add 7 sec waiting time for user input to enter BIOS setup. | BIOS requriement section 2.1
2025-03-21 | P21MT04A | RAS Feature | NV RAS components |  | SIT-2/14: What's the implment status for NVRAStool? BIOS-2/19: Based on the RAS tool user guide, BIOS needs to enable APEI for error injection, and APEI is enabled by default. RAStools also include BMC requirements. After discussing with BMC-Mark, the current BMC should be able to support it. We can discuss with BMC further if got any problem during testing.
|  | Network advanced features | - PXE boot (IPV6) | BIOS Reqirement Section 2.2.11
|  |  | - HTTP boot | BIOS requirement Sectgion 2.2.11 . Including Two OEM IPMI command, NetFN: 0x30, CMD: 0x57/0x58
|  | System management | - update PPIN to SMBIOS type 11 | BIOS Requirement Section 2.5
|  |  | - Communicate to BMC by Send PPIN and GET PPIN | BIOS requirement Section 2.5
|  |  | - POST code, following silicon vendor's Implementation | BIOS requirement Section 2.5
|  | BMC & IPMI advanced requirements | - Wait for BMC IPMI command ready | BIOS requirement Section 2.2.15
|  | System power setting check for match spec define |  | BIOS Requirement section 2.8
Issue fixes
2025-03-28 | P21MT05A | System Components | TPM | BIOS Requirement Section 2.2.9
|  | IPMI CMOS Clear |  | BIOS Requirement Section 2.3.3
|  | FRB2 Watchdog |  | BIOS Requirement Section 2.3.4
|  | BMC & IPMI relate implement | - Send BIOS version to BMC | BIOS requirement Section 2.2.15 NetFN: 0x06, CMD:0x58
|  |  | - Send PCIe Configuraton to BMC | BIOS requirement Section 2.2.15 NetFN:0x30 CMD: 0x71 (OEM command)
|  |  | - Send Boot order to BMC | BIOS requirement Section 2.2.15 NetFN:0x30 CMD: 0x52 (OEM command)
|  | SMBIOS dynamic update | - Update SMBIOS by read FRU.
Issue fixes
2025-04-04 | No Rlease |  |  | 4/3~4/4 Taiwan Holiday
2025-04-11 | P21MT06A | Sytstem Security | UEFI secure boot | BIOS Requirement 2.6
|  | PCIe Managed Power Control(Hotplug) |  | BIOS requirement Section 4.4.3
|  | RAS features behavior and implement check | - Error inject for CPU/PCIE/Memory | - BIOS Requirement section 3 - Following NV Grance RAS feture requirement | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: I will adjust and update the schedule for the RAS features.
|  |  | - Error handling for CPU/PCIe/Memory |  | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: I will adjust and update the schedule for the RAS features.
|  |  | - Error reporting |  | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: I will adjust and update the schedule for the RAS features.
|  |  | - DPC event loging | BIOS requirement Section 4.4.2
|  | OEM SEL Implement | - PCIe error SEL | BIOS Requirement section 5 * UPI Error/IIO Error/UPI/Boot Guard/MCA Error are Intel Platform feture, Not supported in the GB200/GB300 Platform | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: In Nvidia Grace architecture, NV RAS FW notifies BMC about RAS event by using PLDM over MCTP messages. CPU/Memory/PCIe errors are reported to BMC with CPER format, BMC is responsible for RAS error logging, BIOS only reported POST errors.
|  |  | - Memory error SEL |  | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: In Nvidia Grace architecture, NV RAS FW notifies BMC about RAS event by using PLDM over MCTP messages. CPU/Memory/PCIe errors are reported to BMC with CPER format, BMC is responsible for RAS error logging, BIOS only reported POST errors.
- POST Error Event SEL
|  |  | - PCIe device failure events SEL |  | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: In Nvidia Grace architecture, NV RAS FW notifies BMC about RAS event by using PLDM over MCTP messages. CPU/Memory/PCIe errors are reported to BMC with CPER format, BMC is responsible for RAS error logging, BIOS only reported POST errors.
|  |  | - Memory device failure events SEL |  | SIT-2/14: Unable to execute in CP#1 (CP#1 items should completed within 3 weeks) BIOS-2/19: In Nvidia Grace architecture, NV RAS FW notifies BMC about RAS event by using PLDM over MCTP messages. CPU/Memory/PCIe errors are reported to BMC with CPER format, BMC is responsible for RAS error logging, BIOS only reported POST errors.
POST code for error DIMM lication and error code
Issue fixes
2025-04-18 | P21MT07A | System Performance tuning |  | BIOS Requirement Section 2.7
|  | Boot order arrange | - able to set and get BIOS boot order throuth BMC | BIOS Requirement Section 2.3.1.1 NetFN: 0x30 CMD_OEM_SET_BOOT_ORDER 0x52 CMD_OEM_GET_BOOT_ORDER 0x53
|  |  | - Respect omission of DHCPv4 / DHCPv6 if requested | BIOS Requirement Section 2.3.1.1
|  |  | - Not waiting for BMC, BIOS shall clear [boot flags valid(bit7)] when get the command back | BIOS Requirement Section 2.3.1.1
|  |  | - Disabe unuse PXE boot device, only keep the IPV6/IPV4 UEFI on CX7 at CPU0 | Request in visit meeting @ 1/8
|  | Boot Time |  | BIOS Requirement Section 2.3.1.2
Issue fixes
2025-04-25 | P21MT08A | Manufacturing requirement |  | BIOS Requirement 2.9
Issue fixes
2025-05-02 | P21MT09A | Issue fixes

## BIOS Release PlanV1.0
L10 Compute tray Shipment date |  | 2025-02-26
EVT exit Date |  | 2025-05-13
Release Date | Version | Function |  | Comment
2025-03-14 | P21MT01A | Compute tray design porting | - PCIe Bifurcation
- GPIO configuration
- HW design configuraiton
|  | Serial console | - consosle Redirection | BIOS Requirement Section 2.2.10
|  |  | - Serial over lan | BIOS Requirement Section 2.2.10
|  |  | - Output POST code to BMC SOL | BIOS Requirement Section 2.2.15
|  | BIOS upgrade/downgrade |  | BIOS requirement Section 2.3.2
|  | IPMI 2.0 | - SSIF initialization | Grace is use SSIF for IPMI command
|  | System boot | - Boot from HDD/USB device. | BIOS Requirement Section 2.3.1
- efibootmgr
|  | System components information | Initial implement
|  | BIOS setup menu | Initial implement
|  | ACPI tables | Initial implement
|  | SMBIOS structures | Initial implement
|  | Network stack | Initial implement
Bring-up debug support
2025-03-21 | P21MT02A | ACPI implement check |  | BIOS Requirement Section 2.4
|  | SMBIOS implement check |  | BIOS Requirement Section 2.4
|  | RAS Feature | NV RAS components
|  | BIOS setup menu advanced | - Don't show the system information in POST Screen | BIOS requriement section 2.1
|  |  | - Add 7 sec waiting time for user input to enter BIOS setup. | BIOS requriement section 2.1
|  | System Components information implement check | - CPU/Memory/PCIe | BIOS requriement section 2.2
|  |  | - Component information, Display SKU and HW revision in setup menu | BIOS requriement section 2.2.18
|  | Network advanced features | - PXE boot (IPV6) | BIOS Reqirement Section 2.2.11
|  |  | - HTTP boot | BIOS requirement Sectgion 2.2.11 . Including Two OEM IPMI command, NetFN: 0x30, CMD: 0x57/0x58
|  | System management | - update PPIN to SMBIOS type 11 | BIOS Requirement Section 2.5
|  |  | - Communicate to BMC by Send PPIN and GET PPIN | BIOS requirement Section 2.5
|  |  | - POST code, following silicon vendor's Implementation | BIOS requirement Section 2.5
|  | BMC & IPMI advanced requirements | - Wait for BMC IPMI command ready | BIOS requirement Section 2.2.15
|  | System power setting check for match spec define |  | BIOS Requirement section 2.8
Issue fixes
2025-03-28 | P21MT03A | System Components | TPM | BIOS Requirement Section 2.2.9
|  | IPMI CMOS Clear |  | BIOS Requirement Section 2.3.3
|  | FRB2 Watchdog |  | BIOS Requirement Section 2.3.4
|  | BMC & IPMI relate implement | - Send BIOS version to BMC | BIOS requirement Section 2.2.15 NetFN: 0x06, CMD:0x58
|  |  | - Send PCIe Configuraton to BMC | BIOS requirement Section 2.2.15 NetFN:0x30 CMD: 0x71 (OEM command)
|  |  | - Send Boot order to BMC | BIOS requirement Section 2.2.15 NetFN:0x30 CMD: 0x52 (OEM command)
|  | SMBIOS dynamic update | - Update SMBIOS by read FRU.
Issue fixes
2025-04-04 | No Rlease |  |  | 4/3~4/4 Taiwan Holiday
2025-04-11 | P21MT04A | Sytstem Security | UEFI secure boot | BIOS Requirement 2.6
|  | PCIe Managed Power Control(Hotplug) |  | BIOS requirement Section 4.4.3
|  | RAS features behavior and implement check | - Error inject for CPU/PCIE/Memory | - BIOS Requirement section 3 - Following NV Grance RAS feture requirement
- Error handling for CPU/PCIe/Memory
- Error reporting
|  |  | - DPC event loging | BIOS requirement Section 4.4.2
|  | OEM SEL Implement | - PCIe error SEL | BIOS Requirement section 5 * UPI Error/IIO Error/UPI/Boot Guard/MCA Error are Intel Platform feture, Not supported in the GB200/GB300 Platform
- Memory error SEL
- POST Error Event SEL
- PCIe device failure events SEL
- Memory device failure events SEL
POST code for error DIMM lication and error code
Issue fixes
2025-04-18 | P21MT05A | System Performance tuning |  | BIOS Requirement Section 2.7
|  | Boot order arrange | - able to set and get BIOS boot order throuth BMC | BIOS Requirement Section 2.3.1.1 NetFN: 0x30 CMD_OEM_SET_BOOT_ORDER 0x52 CMD_OEM_GET_BOOT_ORDER 0x53
|  |  | - Respect omission of DHCPv4 / DHCPv6 if requested | BIOS Requirement Section 2.3.1.1
|  |  | - Not waiting for BMC, BIOS shall clear [boot flags valid(bit7)] when get the command back | BIOS Requirement Section 2.3.1.1
|  |  | - Disabe unuse PXE boot device, only keep the IPV6/IPV4 UEFI on CX7 at CPU0 | Request in visit meeting @ 1/8
|  | Boot Time |  | BIOS Requirement Section 2.3.1.2
Issue fixes
2025-04-25 | P21MT06A | Manufacturing requirement |  | BIOS Requirement 2.9
Issue fixes
2025-05-02 | P21MT07A | Issue fixes