## Schedule_DVT_PVT
| 2025-05-05 |  |  |  |  | 2025-05-12 |  |  |  |  | 2025-05-19 |  |  |  |  | 2025-05-26 |  |  |  |  | 2025-06-02 |  |  |  |  | 2025-06-09 |  |  |  |  | 2025-06-16 |  |  |  |  | 2025-06-23 |  |  |  |  | 2025-06-30 |  |  |  |  | 2025-07-07 |  |  |  |  | 2025-07-14 |  |  |  |  | Risk
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Bring Up (EE,CPLD,BIOS,BMC) | 2025-05-26 W: Bring Up 5/28 ~ 6/6
DVT BKC Test | 2025-05-05 M: *FW; 2025-05-12 M: BKC PreTest 5/12 ~ 5/23; 2025-05-19 M: *FW; 2025-05-26 W: BKC Test 5/28 ~ 6/6
SMT 5/26 ~ 6/6
DVT L6 Test | 2025-05-26 T: L6 test 5/29 ~ 6/11 | 制具不足 ?
DVT L10 test | 2025-06-09 M: L10 Assambly test 6/9 ~ 6/26
DVT L11 test | 2025-06-09 T: L11 Assambly test 6/10-6/27
DVT Validation | 2025-06-09 M: DVT Validation 6/9 ~ 9/9
PVT BKC Test
PVT L6 Test
PVT L10 test | 2025-06-23 M: L10 Assambly test 6/23 ~ 7/3
PVT L11 test
PVT Validation | 2025-07-07 M: PVT Validation 7/7 ~ 10/9

## Diag_Release_Plan
Diag link | DVT Readiness Plan

## BIOS_Release_Plan
| 2025-06-09 |  |  |  |  | 2025-06-16 |  |  |  |  | 2025-06-23 |  |  |  |  | 2025-06-30 |  |  |  |  | 2025-07-07 |  |  |  |  | 2025-07-14 |  |  |  |  | 2025-07-21 |  |  |  |  | Status | Functon support
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
DVT
CLE202 | 2025-06-09 W: 2025-06-11 | 6/11. update RC verison 2.04.07 | 1. ACPI implement Check . 2 SMBIOS implement Check. 3 RAS Featurer. 4 system components information. 5 system power setting
CLE202 | 2025-06-23 W: 2025-06-25 | update RC version to 2.04.10 | 1. Network stack-HTTP boot. 2. IPMI advanced feature.3 system management
CLE203 | 2025-07-07 W: 2025-07-09 | fix issue | 1. system component- TPM check.2. IPMI CMOS clear. 3. FRB2 WDT. 4. dynbamic SMBIOS update. 5. BIOS setup advanced feature.
CLE204 | 2025-07-21 W: 2025-07-23 | fix issue
PVT
1. support the Bianca GB300. 2. Move the BIOS implementation to Bianca GB300 from Cordelia GB300.
1. POST error Event Sel. 2. send ECID to BMC. 3 OEM IPMI implement.
EVT BIOS release Plan_V1.5.2_20250609A.xlsx

## BMC_Release_Plan
| 2025-04-14 |  |  |  |  | 2025-04-21 |  |  |  |  | 2025-04-28 |  |  |  |  | 2025-05-05 |  |  |  |  | 2025-05-12 |  |  |  |  | 2025-05-19 |  |  |  |  | 2025-05-19 |  |  |  |  | Status | Functon support
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
EVT
clemente-v2025.0.9.Ingrasys | 2025-04-21 M: 2025-04-21 | 4/21 release v2025.0.9 | Fix issue: CGC-52
clemente-v2025.0.10.Ingrasys | 2025-04-21 F: 2025-04-25 | Upload code for Meta review | Merge latest OpenBMC/MetaBMC codebase. Fix major EVT issues, no new features
clemente-v2025.0.11.Ingrasys | 2025-04-28 F: 2025-05-02 |  | Merge latest OpenBMC/MetaBMC codebase. Fix major EVT issues, no new features
DVT
clemente-v2025.1.1.Ingrasys | 2025-05-05 F: 2025-05-09 | To provide FW froe DVT L6 SMT | 1. Integraton of DVT design change, especially for PDB and interposer HW change 2. HGX_GPU reading issue clarify 3. Dual flash recovery
clemente-v2025.1.2.Ingrasys | 2025-05-12 F: 2025-05-16 |  | Merge latest OpenBMC/MetaBMC codebase. Fix major EVT issues 1. Power Control of Host Force Power off/Host Force Restart/Host Force Power off
clemente-v2025.1.3.Ingrasys | 2025-05-19 F: 2025-05-23 |  | 1. Calculate airflow based on fan speeds and hardware presence 2. CX-8 reading be ready/Support CX8 OOB FW update
clemente-v2025.1.4.Ingrasys | 2025-05-19 F: 2025-05-30 | To provide FW for BKC testing | P0/P1 issue be fixed

## RMC_BMC_Release_Plan
| 2025-06-02 |  |  |  |  | 2025-06-09 |  |  |  |  | 2025-06-16 |  |  |  |  | 2025-06-23 |  |  |  |  | 2025-06-30 |  |  |  |  | 2025-07-07 |  |  |  |  | 2025-07-14 |  |  |  |  | 2025-07-21 |  |  |  |  | 2025-07-28 |  |  |  |  | Status | Functon support
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
DVT
ventura-v2025.1.6.Ingrasys | 2025-06-02 F: 2025-06-06 | Update code from upstream on 2025/06/04 | Merge latest LF/FB OpenBMC codebase. Fix issues, no new features
ventura-v2025.1.7.Ingrasys | 2025-06-16 F: 2025-06-20 | Update code from upstream on 2025/06/18 | Merge latest LF/FB OpenBMC codebase. Fix issues, no new features
PVT
ventura-v2025.2.1.Ingrasys | 2025-06-30 F: 2025-07-04 | Update code from upstream on 2025/07/02 | Merge latest LF/FB OpenBMC codebase. Fix issues, no new features
ventura-v2025.2.2.Ingrasys | 2025-07-14 F: 2025-07-18 | Update code from upstream on 2025/07/16 | Merge latest LF/FB OpenBMC codebase. Fix issues, no new features
ventura-v2025.2.3.Ingrasys | 2025-07-28 F: 2025-08-01 | Update code from upstream on 2025/07/30 | Merge latest LF/FB OpenBMC codebase. Fix issues, no new features

## CPLD_Release_Plan
| 2025-06-02 |  |  |  |  | 2025-06-09 |  |  |  |  | 2025-06-16 |  |  |  |  | 2025-06-23 |  |  |  |  | 2025-06-30 |  |  |  |  | 2025-07-07 |  |  |  |  | 2025-07-14 |  |  |  |  | 2025-07-21 |  |  |  |  | 2025-07-28 |  |  |  |  | Status | Functon support
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
DVT
E1.S CPLD update (version B0402) | [45 empty] | relaese | The DVT design change and NV only provide jed file
RMC CPLD update (version 20002) | [45 empty] | released | Quanta update RMC CPLD code version v20001 to v20002 and need Hardware verified
RMC SCM CPLD update (version 00010303) | [45 empty] | 6/20 released | Quanta update RMC CPLD code version v00010201 to v00010202 and need Hardware verified
Interposer CPLD update (version 00010110) | [45 empty] | release | Bypss some state trigger condition and need Hardware verified
SCM CPLD update (version D0010227) | [45 empty] | 6/17 release | Fix reboot issue and need hardware verified
SCM CPLD update (version D0010228) | [45 empty] | 7/4 release | Add force shunt down state | bar: 2025-06-09 M to 2025-06-30 F
Interposer CPLD update (version 00010111) | [45 empty] | 7/4 release | Modified DC off status | bar: 2025-06-09 M to 2025-06-30 F

## OS_Release_Plan
CentOS9 /FBK6.13 | 2025-04-21 |  |  |  |  | 2025-04-28 |  |  |  |  | 2025-05-05 |  |  |  |  | 2025-05-12 |  |  |  |  | 2025-05-19 |  |  |  |  | Status | Functon support
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
EVT / DVT
v1.0.3-eng | 2025-04-21 T: 2025-04-22 | 4/22 release v1.0.3-eng | Integrated FBK 6.13, Integrated OS/NV/third party tools, Known issue: USB is not enabled
v1.0.5-eng4 | 2025-04-28 T: 2025-04-29 |  | Enable PXE boot
v1.0.6 | 2025-05-05 F: 2025-05-11 |  | Integrate NV CUDA/CX7/CX8 driver.
v1.0.7 | 2025-05-19 W: 2025-05-21 |  | Fix issues

## FW_Release_Plan_Sample
| 2025-04-14 |  |  |  |  | 2025-04-21 |  |  |  |  | 2025-04-28 |  |  |  |  | 2025-05-05 |  |  |  |  | 2025-05-12 |  |  |  |  | 2025-05-19 |  |  |  |  | Status | Internal Traker
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
L6/L10 RMC Tray test code development
FW update/check | [30 empty] | 4/14-16 Pending on get the test fixtute from PM/HW | Mail : [Meta GB300] RMC drag tool and validation scope | bar: 2025-04-14 M to 2025-04-14 T
FRU update/check | [30 empty] | 4/16 1. Pending on get the test fixtute from PM/HW 2. Pending on DVT RMC FRU spec from SL Ray | Mail : [Meta GB300] RMC drag tool and validation scope | bar: 2025-04-14 W to 2025-04-14 T
Sensor/GPIO/i2c/serial | [30 empty] | 4/14-16 Pending on get the test fixtute from PM/HW | Mail : [Meta GB300] RMC drag tool and validation scope | bar: 2025-04-14 F to 2025-04-21 T
others scripts | 2025-04-21 T: 2025-04-24 | 4/14-16 Pending on get the test fixture from PM/HW | Mail : [Meta GB300] RMC drag tool and validation scope
SFC-related check (SN) | 2025-04-28 M: 2025-04-28 | 4/14-16 Pending on SFC parsing function ready by MFG IT team | Mail : [GB300 Clemente] SFC requirement
L6/L10 Compute Tray test code development
validate centos PXEboot (cooperate with SW/SIT) | 2025-04-21 M: 2025-04-21; 2025-04-28 W: 2025-04-30 | 4/11 Pending on get the MP3 RSW as test fixture -> 4/14 Get the MP3 and config to the RSW. 4/15 Fail to connect from PXE to MP3. -> Confirm with TE now! 4/21 SW OS team will release CentOS9 (ISO) 4/30 SW OS team will release CentOS9 on PXE
validate ubuntu PXEboot (cooperate with SW/SIT) | [30 empty] | 4/14 Pending on validation | bar: 2025-04-14 M to 2025-05-05 W
FW update | [30 empty] | 4/14 develop finish. 4/15 Pending on validation (Fail to connect from PXE to MP3) | bar: 2025-04-14 M
Stress test | bar: 2025-04-14 M to 2025-04-21 M
Fan duty check | [30 empty] | 4/11-14 Pending on provide the FAN duty table by thermal team -> 4/15 Thermal team provide the Fan duty. | Mail : [GB300 Clemente] FAN vendor’s PWM spec | bar: 2025-04-21 T to 2025-04-21 W
others scripts (FRU/Sensor/Smartlog/dmesg...) | bar: 2025-04-21 T to 2025-04-28 T
Config Check | 2025-04-28 F: 2025-05-02
SFC-related check (SN) | 2025-05-05 W: 2025-05-08 | 4/14-15 Pending on SFC parsing function ready by MFG IT team | Mail : [GB300 Clemente] SFC requirement
L11 test development
L11 RLT test (Integrate RMC+Compute+NVswitch Tray's L10 test code) | 2025-05-05 M: 2025-05-05; 2025-05-19 M: 2025-05-19 | 4/15 Need to confirm with SIT team how to test NVSwith.
AEC test (MP3 RTSW) | 2025-05-12 M: 2025-05-12 | 4/14-16 Pending on get the test fixtute from EPD2 (MP3 RTSW AC config + power supply) 4/15 Try follow BOM to connect the CX8 <-> MP3 and set MP3 Vlan 4/15 Need to confirm the latest rack configuration with SE. (It seems there are 3*MP3 on power rack) : We may need to 3 mp3 as AEC test fixture. | Mail : [Clemente] Diag test fixture demand
Powershelf test (Leveage HPRv3 PSU PMM/PSU test coverage) | [30 empty] | 4/14-15 Pending on get the shipment FW value from SL Ray 4/15 Kui will double confirm with Meta switch team that if we don't need 1* Wdge400/per GB300 rack as powershelf test fixture to ssh PMM/PSU. | Mail : [Clemente]L11 component FW version check | bar: 2025-04-14 M to 2025-05-12 F
MP3 test (Leveage HPRv3 MP3 test coverage) | [30 empty] | 4/14-15 Pending on get the shipment FW value from SL Ray 4/15 Kui will confirm with Meta switch team (RTSW MP3 switch validation spec) - Kui release MP3 test/validation as RSW: https://docs.google.com/presentation/d/1o0NvXHkK_RaX_lYzDHPlZ8rB6N5oQ_p4sjfwtEiWxbU/edit?slide=id.g337dd9210ea_0_31#slide=id.g337dd9210ea_0_31 | Mail : [Clemente]L11 component FW version check | bar: 2025-04-14 M to 2025-05-12 F
- Port mapping test (check each mac address) | bar: 2025-04-14 M to 2025-05-12 F
Mgmt switch test (Arista-FB-7010TX) | [30 empty] | 4/14-15 Pending on get the shipment FW value from SL Ray | Mail : [Clemente]L11 component FW version check | bar: 2025-04-14 M to 2025-05-12 F