## Revision History
Date | Name | Changes
2024-12-18 | Akash Borate | Draft Template to share with Ingrasys
12/28/2024 | Enya Chen | Based on draft template, Ingrasys release inital Clemente build matrix, updated items are marked with red. @Meta PLM and PQE team, there are some open items need Meta help to confirm or clarify, including Mfg PN of commodities parts. (See detail Ingrasys notes in Column I, need Meta help to provide feedback or comment in Column K)
01/08/2025 | Enya Chen | 1). Add "EVT2 Rack config" tab for IGS rack and Meta rack discussion @Meta, need Meta help to reivew and provide Meta rack configuraiton. 2). Add SOCAMM 2nd source (Kingston). 3). Add L10 Compute tray Cables' MPN and ODMPN. 4). Change to Quanta RMC. 5). Add Canister ODMPN. 6). Remove (Row 388-433) as they are included in Canister. 7). Remove Fiber Patch Panel, fiber and transiver. (should be in Side PWR Rack). 8). Based on IT Rack Cable Mapping discussing with Jaret. Add 800G AEC cable, 400G DAC cable and 10G DAC cable. 9). Change 2OU Pizza Box Qty from 1 to 3.
[cont] | Enya Chen | @Michael, there are some parts' MPN need Meta help to confirm - (Row 26-30) 19- GB300 Module w/o cold plate - (Row 32-36) 10-SOCAMM - (Row 46-50) 10-LGA for CX8 - (Row 54-58) 19- NIC Card CX8 Dual Port 200G - (Row 59-63) 19- CX7 Backend NIC, IO board - (Row 64-66) 19- HMC module for GB300 - (Row 69-73) 09- 2TB E1.S boot drive - (Row 74-78) 09- 8TB E1.S SSD - (Row 345-349) 20 - CI NVSO Tray Assy - (Row 355-359) 06- IT Rack Frame - (Row 366-372) Cable Cartridge (Left/Right) - (Row 373-377) 27- ORV3 power shelf rail - (Row 378-382) 27- ORV3 IT rail - (Row 383-387) 27- MiniPack3 Railkit - (Row 434-438) 27- L10 system rail kit - (Row 452-456) 14- Power Shelf - (Row 457-461) 03- PSU (5.5 KW) - (Row 467-476) 07- ORV3 AC input Cable_NEMA-A (right) - (Row 508-512) 20- Management Switch 7010, come with tray - (Row 543-581) 800G AEC, 400G DAC cable and 10G DAC @Akash and Michael, per SOT meeting discussion, Meta will confirm L11 Cable list by 1/10 and update in SOT&Build Matrix. @Kavya, there are some question in need Meta help to clarify, pls see detail IGS notes in Column I

## EVT2 Build Matrix
For Meta
For Ingrasys
Ingrasys | Configuration | Config A
Description
| Rack Qty | 1 | Ingrasys Note | Ingrasys Owner | Meta Note | Status
01-CI Server Chassis (mini-rack) | Category
01- CI Compute Tray Assy | ODM PN | 1A72BSJ00-600-G
FB PN
| Quantity | 3
19-GB300 Module | ODM PN |  | [1/8] IGS suggest remove the level there are no assy MPN include Row16-46. [12/27] Does it mean IGS should be create a subBOM and ODMPN include (Row15-42)? | Thomas Yeh |  | Open
FB PN
| Vendor | NVIDIA
| MPN | [5 empty] | S
| Quantity | 1
05- CPU Coldplate | ODM PN | TEMP-S000225733 | [12/27] IGS update. | Eric Chou |  | Closed
FB PN
| Vendor | Cooler Master
| MPN | LC-04906-01-GP3S1
| Quantity | 2
05- GPU Coldplate | ODM PN | TEMP-S000225734 | [12/27] IGS update. | Eric Chou |  | Closed
FB PN
| Vendor | Cooler Master
| MPN | LC-04907-01-GP3S1
| Quantity | 4
19- GB300 Module w/o cold plate | ODM PN | TEMP-S000225738 | [12/27] Need Meta confirm the Mfg PN | Thomas Yeh |  | Open
FB PN
| Vendor | NVIDIA
| MPN | 675-24480-0000-ES1
| Quantity | 1
11-Grace ARM | ODM PN |  | [12/27] It should be Included in GB300 Module (Row25-29), Nvida consign | Thomas Yeh |  | Open
FB PN
Vendor
MPN
| Quantity | 1
10-SOCAMM | ODM PN | Micron: TEMP-S000225747 Kingston: TEMP-S000226361 | [1/8] Add Second Source. [12/27] IGS update. Need Meta help to confirm MPN | Thomas Yeh |  | Open
FB PN
| Vendor | Micron/Kingston
| MPN | Micron: MT62F8G32DADV-026DWT:F Kingston: NV064SC8G32MB-128
| Quantity | 8
10-LGA SOCAMM | ODM PN | Lotes: TEMP-S000226158 FIT: TEMP-S000226159 | [1/8] IGS Update.MPN Information from Meta. | Thomas Yeh |  | Closed
FB PN
| Vendor | Lotes/FIT
| MPN | Lotes: ACAM0018-P005C06C FIT: PL06946-12NN0-4H
| Quantity | 8
10-LGA Interposer 10-LGA for CX8 | ODM PN | TEMP-S000226160 | [1/8] IGS Update. Need Meta help to confirm MPN | Thomas Yeh |  | Open
FB PN
| Vendor | Foxconn
| MPN | PL08517-12NN0-4H
| Quantity | 2
19-GPU Chip | ODM PN |  | [12/27] It should be Included in GB300 Module (Row25-29), Nvida consign | Thomas Yeh |  | Open
FB PN
| Quantity | 1
19- NIC Card CX8 Dual Port 200G | ODM PN | TEMP-S000225739 | [12/27] Need Meta confirm the Mfg PN | Thomas Yeh |  | Open
FB PN
| Vendor | NVIDIA
| MPN | 900-9X88E-00CX-SP0
| Quantity | 2
19- Backend NIC, IO board 19- CX7 Backend NIC, IO board | ODM PN | AD002476012 TEMP-S000226360 | [1/8] IGS Update. [12/27] Could Meta help to provdie Mfg PN? | Thomas Yeh |  | Open
FB PN
| Vendor | NVIDIA
| MPN | CX75343AMC-NEAC_FB
| Quantity | 2
19- HMC module for GB300 | ODM PN | TEMP-S000225740 | [12/27] Need Meta confirm the Mfg PN | Thomas Yeh |  | Open
FB PN
| Vendor | NVIDIA
| MPN | 699-24764-0004-ES1
| Quantity | 1
09- 2TB E1.S boot drive | ODM PN | Samsung: TEMP-S000225741 Micron: TEMP-S000225742 Kioxia: TEMP-S000225743 | [12/27] Information from Meta Catherine. | Thomas Yeh |  | Closed
FB PN
| Vendor | Samsung/Micron/Kioxia
| MPN | Samsung: MZTL61T9HFJA-00AFB Micron: MTFDKBT1T9TFR-1BC4DABVA Kioxia: KXDZDRJJ1T92
| Quantity | 1
09- 8TB E1.S SSD | ODM PN | Samsung: TEMP-S000225744 WD: TEMP-S000225745 Micron: TEMP-S000225746 | [12/27] Informamtionn from Meta Catherine. The system spec from Meta is 16TB, but this SSDs' spec is 8TB need Meta to clarify whitch is correct | Thomas Yeh |  | Open
FB PN
| Vendor | Samsung/WD/Micron
| MPN | Samsung: MZOL67T6HBLC-00AFB WD: WUS6A7676PJP8X7 Micron: MTFDLBU7T6THC-1BK4FABVA
| Quantity | 4
19- PDB | ODM PN | PDB Brick: 1A72BTF00-600-G PDB Discrete: 1A72BTF00-600-G | [12/27] IGS update | Thomas Yeh |  | Closed
FB PN
| Quantity | 1
19- FAN Board_R | ODM PN | 1A72BTG00-600-G | [12/27] IGS update | Thomas Yeh |  | Closed
FB PN
| Quantity | 1
19- FAN Board_L | ODM PN | 1A72BT500-600-G | [12/27] IGS update | Thomas Yeh |  | Closed
FB PN
| Quantity | 1
19- FIO board | ODM PN | 1A72BTH00-600-G | [12/27] IGS update | Thomas Yeh |  | Closed
FB PN
| Quantity | 1
19- DC-SCM 2.0 (include 2*TPM+1*BSM+1*Sensor board) | ODM PN | 1A72BTC00-600-G | [12/27] IGS update | Thomas Yeh |  | Closed
FB PN
| Quantity | 1
19- HDD BP (E1.S midplane) 19-E1.S backplane | ODM PN | 1A72BTD00-600-G | [12/27] IGS update | Thomas Yeh |  | Closed
FB PN
| Quantity | 1
19- OSFP carrier board | ODM PN | 1A72BTJ00-600-G | [12/27] IGS update | Thomas Yeh |  | Closed
FB PN
| Quantity | 1
19- HSC Board | ODM PN | TEMP-S000225793 1A72CF700-600-G | [1/8] IGS update. | Thomas Yeh |  | Closed
FB PN
| Quantity | 1
05- FAN 4056 | ODM PN | TEMP-S000225519/TEMP-S000225520 | [12/27] IGS update | Alan Chang |  | Closed
FB PN
| Vendor | AVC/Sunon
| MPN | DFPQ0456B2GY081/XG40561BX-1Q991-S9W
| Quantity | 8
05- L10 Manifold (hot and cold, 1 set) | ODM PN | TEMP-S000225735 | [12/27] IGS update | Alan Chang |  | Closed
FB PN
| Vendor | Cooler Master
| MPN | LC-04915-01-GP3S1
| Quantity | 1
07- Fan extend cble | ODM PN
FB PN
Vendor
MPN
| Quantity | 1
07- HDDBD Power cable 07- 54V Power connector | ODM PN | TEMP-S000225990 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HWHHW-BA88
| Quantity | 1
07- RJ 45 Front panel cable 07- DC-SCI cable | ODM PN | TEMP-S000225991 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HGZ168-1229
| Quantity | 1
07- Leakage sensor cable_1 07- DC-SCM2.0 cable | ODM PN | TEMP-S000225992 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HGZ168-1230
| Quantity | 1
07- Leakage sensor cable_2 07- NIC0 3-to-1 cable | ODM PN | TEMP-S000225994 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HGZ168-1231
| Quantity | 1
07- Leakage sensor cable_3 07- NIC1 3-to 1 cable | ODM PN | TEMP-S000225993 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HGZ168-1232
| Quantity | 1
07- Leakage sensor cable_4 07- Front IO board SlimSAS | ODM PN | TEMP-S000225995 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HSL38-4032
| Quantity | 1
07- 5 way cable (MCIO 38 Pin, MCIO x8, MCIO 148 Pin, Genz 4C+NIC1 power and sideband) 07- E1.S Backplane power cable | ODM PN | TEMP-S000225996 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HWHHW-BA89
| Quantity | 1
07- 5 way cable (MCIO 38 Pin, MCIO x8, MCIO 148 Pin, Genz 4C+NIC0 power and sideband) 07- E1.S Backplane MCIO Y cable 1 | ODM PN | TEMP-S000225997 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HMC74-C264
| Quantity | 1
07- SlimSAS 74Pin to DC-SCI cable 07- E1.S Backplane MCIO Y cable 2 | ODM PN | TEMP-S000225998 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HMC74-C265
| Quantity | 1
07- SlimSAS 124Pin cable 07- OSFP PWR cable | ODM PN | TEMP-S000225999 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HWHHW-BA90
| Quantity | 1
07- GenZ 4C + cable 07- OSFP sideband cable 1 | ODM PN | TEMP-S000226000 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HWHHW-BA91
| Quantity | 1
07- HMC MCIOx8 Cable1 07- OSFP sideband cable 2 | ODM PN | TEMP-S000226001 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HWHHW-BA92
| Quantity | 1
07- HMC MCIOx8 Cable0 07- E1.S SSD Y cable | ODM PN | TEMP-S000226109 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HGZ56-0922
| Quantity | 1
07- Right OSFP Sideband cable | ODM PN
FB PN
| Vendor | GLE
MPN
| Quantity | 1
07- Left OSFP Sideband cable | ODM PN
FB PN
| Vendor | GLE
MPN
| Quantity | 1
07- Right OSFP Overpass cable 1 | ODM PN |  | [1/8] Deleted since it will put in OSFP board L6
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- Right OSFP Overpass cable 0 | ODM PN |  | [1/8] Deleted since it will put in OSFP board L6
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- Left OSFP Overpass cable 1 | ODM PN |  | [1/8] Deleted since it will put in OSFP board L6
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- Left OSFP Overpass cable 0 | ODM PN |  | [1/8] Deleted since it will put in OSFP board L6
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- PDB Sideband cable 07- Leakage sensor cable 1 | ODM PN | TEMP-S000226002 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HWHHW-BA93
| Quantity | 1
07- GB200 Stby power cable 07- Leakage sensor cable 2 | ODM PN | TEMP-S000226003 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HWHHW-BA94
| Quantity | 1
07- OSFP Power cable 07- Leakage sensor cable 3 | ODM PN | TEMP-S000226004 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HWHHW-BA95
| Quantity | 1
07- Radsok Power Cable (2+2) 07- Leakage sensor cable 4 | ODM PN | TEMP-S000226005 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HWHHW-BA96
| Quantity | 1
07- Radsok Power Cable (3+3) 07- Hotswap sideband cable | ODM PN | TEMP-S000226110 | [1/8] IGS update MfgPN and ODMPN [12/27] IGS update Interal cable list. Will provide MfgPN and ODMPN. | Thomas Yeh |  | Closed
FB PN
| Vendor | Amphenol
| MPN | HWHHW-BB41
| Quantity | 1
07- 54V Busbar Clip | ODM PN | TEMP-S000226119 | [1/8] IGS update. | Thomas Yeh |  | Closed
FB PN
| Vendor | TE
| MPN | 2498786-1
| Quantity | 1
27- Compute Tray Assy | ODM PN
FB PN
| Quantity | 1
27- MB Carrier Assy | ODM PN
FB PN
| Quantity | 2
Coolant | ODM PN
FB PN
| Quantity | 0
01- CI RMC Tray Assy | ODM PN | TEMP-S000226516 | [1/8] IGS update. EVT2 phase will use Qunta RMC. [12/28] Follow GB200, IGS will update RMC build matrix once GB200 build matrix completed. | Thomas Yeh |  | Closed
FB PN
| Vendor | Qunta
| MPN | 3RL05MA0010
| Quantity | 1
19- RMC_LED_board | ODM PN
FB PN
| Quantity | 1
19- RMC rear I/O BD | ODM PN
FB PN
| Quantity | 1
19-Rack Management Controller Board | ODM PN
FB PN
| Quantity | 1
05- Fan board | ODM PN
FB PN
| Quantity | 2
19-DC-SCM 2.0 (include TPM+BSM+Sensor board) | ODM PN
FB PN
| Quantity | 1
05- FAN 4056 | ODM PN | TEMP-S000222166/ TEMP-S000222167
FB PN
| Vendor | AVC/Sunon
| MPN | DFPQ0456B2GY079/XG40561BX-1Q979-S9W
| Quantity | 4
07- Fan signal cable_1 | ODM PN
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- Fan power cable_1 | ODM PN
FB PN
| Vendor | GLE
MPN
| Quantity | 1
07- Rear IO Singal cable | ODM PN
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- Rear IO Power cable | ODM PN
FB PN
| Vendor | GLE
MPN
| Quantity | 1
07- RMC LCCU internal Power cable (Cold & hot water) | ODM PN
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- RMC LCCU internal Power cable_0 | ODM PN
FB PN
Vendor
MPN
| Quantity | 1
07- Leak detection cable_1 | ODM PN | DQ900AA0800
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- Leak detection cable_2 | ODM PN |  | Follow GB200, remove leak detection cable
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- Leak detection cable_3 | ODM PN |  | Follow GB200, remove leak detection cable
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- 48V Busbar cable | ODM PN
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- Fan signal cable_0 | ODM PN
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- Fan power cable_0 | ODM PN
FB PN
| Vendor | GLE
MPN
| Quantity | 1
27- Metal Chassis | ODM PN
FB PN
| Quantity | 1
27- RMC fan carrier | ODM PN
FB PN
| Quantity | 1
20 - CI NVSO Tray Assy | ODM PN | TEMP-S000225750 | [1/8] IGS update ODMPN. Need Meta confirm MPN. [12/27] IGS update, Need Meta confirm MPN | Jessy Chang |  | Open
| FB PN | TBD
| Vendor | NVIDIA
| MPN | 920-9K33R-00MV-ES1
| Quantity | 1 9
27- Chassis Mechanical | ODM PN |  | [1/8] The part is Canister (same as Row358-360), remove this parts. | Jessy Chang |  | Closed
FB PN
| Quantity | 1
55 - Rack & Power Sub-assy | Quantity | 1
06- HPR 80KW Rack Frame 06- IT Rack Frame | ODM PN | TEMP-S000226517 | [1/8] IGS update Mfg/MFg PN and ODMPN, Need Meta help to Confirm MPN. | Jessy Chang |  | Open
FB PN
| Vendor | Rittal
| MPN | 7844664
| Quantity | 1
Canister | ODM PN | 1A72B7000-600-G 1A72B7000-600-G1 | [1/8] IGS update ODMPN. [12/27] Follow Catalina, IGS update. Will interal recheck | Jessy Chang |  | Closed
| FB PN | 27-100238
| Quantity | 1
Fiber Patch Panel (1OU) | ODM PN | TEMP-S000222270 | [1/8] Remove, FPP is at Side Power Rack [12/27] Ref Catalina, IGS update. Need Meta confirm the MPN. | Jessy Chang |  | Closed
| FB PN | 23-103173
| Vendor | Corning
| MPN | FC-F-01OU128MCA
| Quantity | 1
Cable Cartridge (Left/Right) | ODM PN |  | [1/8] IGS update Mfg/MFg PN. Need Meta help to Confirm MPN. | Jessy Chang |  | Open
FB PN
| Vendor | NVIDIA
| MPN | 965-24972-0020-000
| Quantity | 1 4
27- ORV3 power shelf rail | ODM PN | TEMP-S000222271 | [1/8] IGS update Qty to 4. Need Meta confirm MPN. - 4 pcs = 4*Power Shelf [12/27] Ref Catalina, IGS update. Need Meta confirm the MPN. 1*RMC+1*Management SW+1*Minipack3+1*1OU Pizza Box+1*2OU Pizza box | Jessy Chang |  | Open
| FB PN | 27-001501
| Vendor | Rittal
| MPN | 7844557
| Quantity | 4
27- ORV3 IT rail | ODM PN | TEMP-S000222274 | [1/8] IGS update Qty to 6. Need Meta confirm MPN. - 6 pcs = 1*1OU Pizza + 3*2OU pizza box + 1*RMC + 1*Management SW [12/27] Ref Catalina, IGS update. Need Meta confirm the MPN.. 4*Supercap+4*Power shelf | Jessy Chang |  | Open
| FB PN | 27-001499
| Vendor | Rittal
| MPN | 7844556
| Quantity | 6
27- MiniPack3 Railkit | ODM PN |  | [1/8] IGS adds the Item and MPN PN from Catherine. | Jessy Chang |  | Closed
| FB PN | 27-100124
| Vendor | KingSlide
| MPN | U602-625-IM
| Quantity | 1
27- Left Adapter Bracket Pre-assembly | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Quantity | 1
27- Right Adapter Bracket Pre-assembly | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Quantity | 1
27- Cartridge support bracket | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Quantity | 1
27- Support Bracket | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Quantity | 1
27- Drip tray | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Quantity | 1
27- Top front_Rack Stiffener | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Quantity | 1
27- Top back_Rack Stiffener | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Quantity | 1
27- Bottom front_Rack Stiffener | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Quantity | 1
27- Bottom back_Rack Stiffener | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Quantity | 1
Rack Manifold with Bracket _left | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Vendor | Cooler Master
MPN
| Quantity | 1
Rack Manifold with Bracket _right | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Vendor | Cooler Master
MPN
| Quantity | 1
27- Top Scale out Eject Bar | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Quantity | 2
27- Middle Scale out Eject Bar | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Quantity | 2
27- Bottom Scale out Eject Bar | ODM PN |  | [1/8] Remove, it is included in Canister | Jessy Chang |  | Closed
FB PN
| Quantity | 2
27- L10 system rail kit | ODM PN | TEMP-S000222734 TEMP-S000222735 TEMP-S000222736 | [1/8] IGS fill in MFG/MPN. Need Meta confirm MPN. [12/27] Ref Catalina, IGS update | Jessy Chang |  | Open
| FB PN | 27-100239
| Vendor | Kingslide
| MPN | Kingslide: A5682627DPZZBNQ Kingslide: A5682627DPZZANQ Kingslide: A5682627CPZZ1NP
| Quantity | 27
Hot Manifold | ODM PN | TEMP-S000221562 | [12/27] IGS update | Eric |  | Closed
FB PN
| Vendor | CoolerMaster/AVC
| MPN | LC-04541-03-GP2S3/
| Quantity | 1
Cold Manifold | ODM PN | TEMP-S000221560 | [12/27] IGS update | Eric |  | Closed
FB PN
| Vendor | CoolerMaster/AVC
| MPN | LC-04540-03-GP2S3/
| Quantity | 1
Liquid Tube to AALC | ODM PN |  | [1/8] Remove.Not in IT rack. | Jessy Chang |  | Closed
FB PN
| Quantity | 1
14- Power Shelf | ODM PN |  | [12/27] IGS update. Need Meta confirm the MPN. | Jessy Chang |  | Open
| FB PN | 14-100015
| Vendor | AEI
| MPN | 700-037148-1000
| Quantity | 4
03- PSU (5.5 KW) | ODM PN |  | [12/27] IGS update. Need Meta confirm the MPN. | Jessy Chang |  | Open
| FB PN | 03-100049
| Vendor | AEI
| MPN | 700-037147-0000
| Quantity | 24
14- BBU Shelf | ODM PN
FB PN
| Vendor | Panasonic
MPN
| Quantity | 3
07- ORV3 AC input Cable_NEMA-A (left) | ODM PN | TEMP-S000222276
| FB PN | 07-100165
| Vendor | Amphenol
| MPN | 10175249-C78303
| Quantity | 6
07- ORV3 AC input Cable_NEMA-A (right) | ODM PN | TEMP-S000222277
| FB PN | 07-100169
| Vendor | Amphenol
| MPN | 10175743-C78303
| Quantity | 6
07- ORV3 AC input Cable_NEMA | ODM PN
FB PN
| Quantity | 6
54 - Network Sub-assy | Quantity | 1
07- RS485_0.5M - 2 for Power Shelf - 2 for BBU Shelf | ODM PN
FB PN
| Quantity | 4
07- RS485_1.5M - PSU to Wedge400 (upper x 1, lower x 1) - BBU to Wedge400 (upper x 1, lower x 1) | ODM PN
FB PN
| Quantity | 4
20- Wedge 400 | ODM PN
FB PN
| Vendor | Celestica
| MPN | R4018-F1051-04
| Quantity | 2
27- Wedge 400 Tray | ODM PN
FB PN
| Vendor | Celestica
| MPN | 3PL07TA0050
| Quantity | 2
27- Minipack 3 20 - Minipack3 ORV3 DC bundle (include PSU + power cord) | ODM PN | TEMP-S000224821 | [1/8] IGS update description.Mfg PN has confirmed by Catherine [12/27] IGS update. Need Meta help to confirm MPN | Jessy Chang |  | Closed
FB PN
| Vendor | Celestica
| MPN | R3214-F9013-A3
| Quantity | 1
27- Minipack 3 DC PSU Kit 27- MiniPack3 Outer shelf | ODM PN |  | [1/8] IGS update description and MPN. MPN has confirmed by Catherine. [12/27] IGS update. Need Meta help to confirm if this part need to be used and MPN. | Jessy Chang |  | Closed
FB PN
| Vendor | Celestica
| MPN | R3214-F8005-A1 R4002-F0101-03
| Quantity | 1
20- Management Switch 7010, come with tray | ODM PN | TEMP-S000222287 | [12/27] Ref Catalina, IGS update. Need Meta help to confirm MPN. | Jessy Chang |  | Open
| FB PN | 20-100100
| Vendor | Arista
| MPN | FB-7010TX-48C-DC-RV3-F
| Quantity | 1
27- Management Switch Tray | ODM PN
FB PN
Vendor
MPN
| Quantity | 1
27- NV Switch Tray with slides | ODM PN |  | [1/8] Remove as NV switch is at Row345-349. | Jessy Chang |  | Closed
FB PN
| Vendor | NVIDIA
MPN
| Quantity | 1
24- Optics- tranceiver | ODM PN | TEMP-S000224305 | [1/8] Remove the part as Fiber Patch Panel is at Side Power Rack. [12/27] Ref Catalina, IGS update. Need Meta help to confirm MPN. | Jessy Chang |  | Open
| FB PN | 24-000842
| Vendor | NVIDIA
| MPN | 980-9I31N-00NM00
| Quantity | 4
07- 400G Fiber Cable - Compute Tray to Fiber PP L=2800 (L2=600mm) | ODM PN |  | [1/8] Remove the part as Fiber Patch Panel is at Side Power Rack. | Jessy Chang |  | Closed
FB PN
| Vendor | Corning
MPN
| Quantity | 40
07- 400G Fiber Cable - Compute Tray to Fiber PP L=3600 (L2=1000mm) | ODM PN |  | [1/8] Remove the part as Fiber Patch Panel is at Side Power Rack. | Jessy Chang |  | Closed
FB PN
| Vendor | Corning
MPN
| Quantity | 32
07- 400G Fiber Cable - Compute Tray to Fiber PP L=3600 (L2=600mm) | ODM PN |  | [1/8] Remove the part as Fiber Patch Panel is at Side Power Rack. | Jessy Chang |  | Closed
FB PN
| Vendor | Corning
MPN
| Quantity | 32
07- 800G AEC/DAC ( Compute/GPU tray to MP3 RTSW) - 2m | ODM PN |  | [1/8] IGS update. Need Meta confirm MPN and final Rack connection. | Jessy Chang |  | Open
FB PN
| Vendor | Credo/Molex
| MPN | Credo: CAC82X321A1B-C1-HW Molex: 2253611201
| Quantity | 48
07- 800G AEC/DAC ( Compute/GPU tray to MP3 RTSW) - 2.2m | ODM PN |  | [1/8] IGS update. Need Meta confirm MPN and final Rack connection. | Jessy Chang |  | Open
FB PN
| Vendor | Credo/Molex
| MPN | Credo: CAC822321A1B-C1-HW Molex: 2253611201
| Quantity | 24
07- 200G DAC Cable - Compute Tray to Wedge400, 1M 07- 400G DAC Cable - Compute Tray to RSW - 1.1m | ODM PN |  | [1/8] IGS update. Need Meta confirm MPN and final Rack connection. | Jessy Chang |  | Open
FB PN
Vendor
MPN
| Quantity | 20
07- 400G DAC Cable - Compute Tray to RSW - 1.2m | ODM PN |  | [1/8] IGS update. Need Meta confirm MPN and final Rack connection. | Jessy Chang |  | Open
FB PN
Vendor
MPN
| Quantity | 11
07- 400G DAC Cable - Compute Tray to RSW - 1.2m | ODM PN |  | [1/8] IGS update. Need Meta confirm MPN and final Rack connection. | Jessy Chang |  | Open
FB PN
Vendor
MPN
| Quantity | 5
07- 10G DAC - RESW to RMC - 2.5m | ODM PN | TEMP-S000222299 | [1/8] IGS update. Need Meta confirm MPN and final Rack connection. | Jessy Chang |  | Open
FB PN
| Vendor | LXP
| MPN | L02SF085-SD-H
| Quantity | 1
07- 10G DAC - RESW to RSW - 2.5m | ODM PN | TEMP-S000222299 | [1/8] IGS update. Need Meta confirm MPN and final Rack connection. | Jessy Chang |  | Open
FB PN
| Vendor | LXP
| MPN | L02SF085-SD-H
| Quantity | 1
07- 10G DAC - RESW to Side Power Rack RSW - 4.5m | ODM PN |  | [1/8] IGS update. Need Meta confirm MPN and final Rack connection. | Jessy Chang |  | Open
FB PN
Vendor
MPN
| Quantity | 1
07- GB300 Stby power cable | ODM PN
FB PN
| Vendor | Amphenol
MPN
| Quantity | 8
07- 10G DAC - RMC to Wedge400 | ODM PN
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- 10G DAC - Management Switch to Wedge400_RSW1 | ODM PN
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- 10G DAC - Management Switch to Wedge400_RSW2 | ODM PN
FB PN
| Vendor | Amphenol
MPN
| Quantity | 1
07- RJ45 Cable - Compute Tray to RMC L1 | ODM PN
FB PN
| Quantity | 8
07- RJ45 Cable - Compute Tray to RMC L2 | ODM PN
FB PN
| Quantity | 4
07- RJ45 Cable - Compute Tray to RMC L3 | ODM PN
FB PN
| Quantity | 6
07- RJ45 Cable - NVSW_BMC to Management Switch | ODM PN
FB PN
| Quantity | 9
07- RJ45 Cable - NVSW_CP to Management Switch | ODM PN
FB PN
| Quantity | 9
07- 1.6T DAC Cable - Rack1_NVSW to Rack2_NVSW | ODM PN
FB PN
Vendor
| MPN | Amphenol
| Quantity | 162 per 2 Racks
07- RJ45 Cable - Wedge400_RSW2 to Power shelf-1 | ODM PN
FB PN
| Quantity | 1
07- RJ45 Cable - Power shelf-1 to Power shelf-2 & Power shelf-2 to Power shelf-3 | ODM PN
FB PN
| Quantity | 2
07- RJ45 Cable - Wedge400-RSW2 to BBU-1 | ODM PN
FB PN
| Quantity | 1
07- RJ45 Cable - BBU-1 to BBU-2 & BBU-2 to BBU-3 | ODM PN
FB PN
| Quantity | 2
07- RJ45 Cable - Rack1_MGNT Switch to Rack2_MGNT switch | ODM PN
FB PN
| Quantity | 2 per 2 Racks
07- RJ45 Cable - Rack1_RMC to AALC | ODM PN
FB PN
| Quantity | 2
07- RJ45 Cable - Rack2_RMC to AALC | ODM PN
FB PN
| Quantity | 2
07- RJ45 Cable - AALC1_PSU to Rack1_Wedge400 | ODM PN
FB PN
| Quantity | 1
07- RJ45 Cable - AALC2_PSU to Rack1_Wedge400 | ODM PN
FB PN
| Quantity | 1
07- RJ45 Cable - AALC3_PSU to Rack2_Wedge400 | ODM PN
FB PN
| Quantity | 1
07- RJ45 Cable - AALC4_PSU to Rack2_Wedge400 | ODM PN |  | f
FB PN
| Quantity | 1
07- leakage detection RJ45 Cable - Swtich Tray to RMC | ODM PN
FB PN
| Quantity | 9
1 GBE and 1 Console to TOR PON device | ODM PN
FB PN
| Quantity | 2
1 GBE and 1 Console to TOR PON device | ODM PN
FB PN
| Quantity | 9x2
1 GBE and 1 Console to TOR PON device | ODM PN
FB PN
| Quantity | 2x2
1 GBE to PON device | ODM PN
FB PN
| Quantity | 1
Coolant, ship in Wet - NV tray and the rest of L11 | Quantity | ea
26- Rack Packing_with Wooden Crate | Quantity | 1
1OU Air Baffle 1OU Pizza Box | ODM PN | TEMP-S000223211 | [12/27] IGS update. | Jessy Chang |  | Closed
| FB PN | 05-000676
| Vendor | Blue Rose Packaging
| MPN | BRP-61425.ARB
| Quantity | 1
2OU Pizza Box | ODM PN | TEMP-S000223212 | [1/9] IGS update Qty to 3. [12/27] IGS update. | Jessy Chang |  | Closed
| FB PN | 05-000677
| Vendor | Blue Rose Packaging
| MPN | BRP-63320.ARB
| Quantity | 1 3

## EVT2 Rack config
EVT2 Rack config (Foxconn Rack) |  |  |  | EVT2 Rack config (Meta Rack) Not Defined yet
U44 | Rack Management Conroller | U44 |  | U44 | Rack Management Conroller | U44
U43 | 2OU Air Baffle | U43 | not assy Suppercap shelf in EVT2 | U43 | 2OU Air Baffle | U43
U42 |  | U42 | not assy Suppercap shelf in EVT2 | U42 |  | U42
U41 | Power Shelf_1 | U41 |  | U41 | Power Shelf_1 | U41
U40 | Power Shelf_2 | U40 |  | U40 | Power Shelf_2 | U40
U39 | Minipack 3/ FE RSW | U39 |  | U39 | Minipack 3/ FE RSW | U39
U38 |  | U38 |  | U38 |  | U38
U37 |  | U37 |  | U37 |  | U37
U36 |  | U36 |  | U36 |  | U36
U35 | Compute Tray-18 | U35 |  | U35 |  | U35
U34 | Compute Tray-17 | U34 |  | U34 |  | U34
U33 | Compute Tray-16 | U33 |  | U33 |  | U33
U32 | Compute Tray-15 | U32 |  | U32 |  | U32
U31 | Compute Tray-14 | U31 |  | U31 |  | U31
U30 | Compute Tray-13 | U30 |  | U30 |  | U30
U29 | Compute Tray-12 | U29 |  | U29 |  | U29
U28 | Compute Tray-11 | U28 |  | U28 |  | U28
U27 | Compute Tray-10 | U27 |  | U27 |  | U27
U26 | Compute Tray-09 | U26 |  | U26 |  | U26
U25 | Swtich Tray-09 | U25 |  | U25 | Swtich Tray-09 | U25
U24 | Swtich Tray-08 | U24 |  | U24 | Swtich Tray-08 | U24
U23 | Swtich Tray-07 | U23 |  | U23 | Swtich Tray-07 | U23
U22 | Swtich Tray-06 | U22 |  | U22 | Swtich Tray-06 | U22
U21 | Swtich Tray-05 | U21 |  | U21 | Swtich Tray-05 | U21
U20 | Swtich Tray-04 | U20 |  | U20 | Swtich Tray-04 | U20
U19 | Swtich Tray-03 | U19 |  | U19 | Swtich Tray-03 | U19
U18 | Swtich Tray-02 | U18 |  | U18 | Swtich Tray-02 | U18
U17 | Swtich Tray-01 | U17 |  | U17 | Swtich Tray-01 | U17
U16 | Compute Tray-08 | U16 |  | U16 |  | U16
U15 | Compute Tray-07 | U15 |  | U15 |  | U15
U14 | Compute Tray-06 | U14 |  | U14 |  | U14
U13 | Compute Tray-05 | U13 |  | U13 |  | U13
U12 | Compute Tray-04 | U12 |  | U12 |  | U12
U11 | Compute Tray-03 | U11 |  | U11 | Compute Tray-03 | U11
U10 | Compute Tray-02 | U10 |  | U10 | Compute Tray-02 | U10
U9 | Compute Tray-01 | U9 |  | U9 | Compute Tray-01 | U9
U8 | 1OU Air Baffle | U8 |  | U8 | 1OU Air Baffle | U8
U7 | Management SW (RESW) | U7 |  | U7 | Management SW (RESW) | U7
U6 | 2OU Air Baffle | U6 |  | U6 | 2OU Air Baffle | U6
U5 |  | U5 |  | U5 |  | U5
U4 | Power Shelf_3 | U4 |  | U4 | Power Shelf_3 | U4
U3 | Power Shelf_4 | U3 |  | U3 | Power Shelf_4 | U3
U2 | 2OU Air Baffle | U2 | not assy Suppercap shelf in EVT2 | U2 | 2OU Air Baffle | U2
U1 |  | U1 | not assy Suppercap shelf in EVT2 | U1 |  | U1