## L10_BOM_Release_Summary
BOM Version | Release Date | New Added Item & Reason | Usage Change & Reason | Deleted Item & Reason
Clemente-System_L10-BOM-SE-PVT-X06_20250519 | 5/19 | Update backplane, PDB, Interposer to PVT AAPN Update E1.S 25mm Module bracket (per META directive) Update cable 2nd source (29 items) | None | None
Clemente-System_L10-BOM-SE-PVT-X07_20250521 | 5/21 | Update E1.S 25mm Module Screw, QD Gasket (local source) Update label status (SE & META discussion) Update cable 2nd source (5 items) Add acetate tape for leakage sensor cable | None | None
Clemente-System_L10-BOM-SE-PVT-X08_20250522 | 5/22 | Update Dual ConnectX-8 Mezzanine card (PN 900-9X86E-A5CX-ST0) Update 2P Management Crossover Cable 2nd source (1 item) Add CR coin lithium battery Update SSD holder, latch Update RJ45 cable (FRU) | None | None
Clemente-System_L10-BOM-SE-PVT-X09_20250523 | 5/23 | None | Update SSD screw and quantity (FRU, actual situation) | None
Clemente-System_L10-BOM-SE-PVT1-X10_20250526 | 5/26 | Update QD and manifold screws (local source) Update leakage sensor cable 2nd source (4 items) | None | None

## L11_BOM_Release_Summary
BOM Version | Release Date | New Added Item & Reason | Usage Change & Reason | Deleted Item & Reason
Clemente-System_L11 BOM-SE-PVT-NSF-X04_20250520 | 5/20 | None | 1A72EFA00-600-G, 01_top-slim-vcm-28u-b_clc.asm (Quantity, 2 --> 1 , PM instructions) | Remove: 1A72EF300-600-G, 01_top-slim-vcm-28u-baying_clc.asm (PM instruction)
Clemente-System_L11 BOM-SE-PVT-NSF-X05_20250522 | 5/22 | Add Label: LBL, AC Whip + Rack Frame SN Label; LBL. Rack Level SN Label (Discussion with META) | None | None
Clemente-System_L11 BOM-SE-PVT-NSF-X06_20250523 | 5/23 | Update VALVES-WITH-BARBED-FITTING, 7mm local source (Supplier update) | None | None
Clemente-System_L11 BOM-SE-PVT-NSF-X07_20250603 | 6/03 | Add GB300 - CRATED and Crate-less Packaging (PM instruction) | None | None

## RMC_L10_BOM_Summary
BOM Version | Release Date | New Added Item & Reason | Usage Change & Reason | Delete Item & Reason
Clemente-System_RMC L10 BOM-SE-PVT-X02_20250520 | 5/20 | Add LED Board Screw local source. (update procurement provides screws local source information) | None | None
Clemente-System_RMC L10 BOM-SE-PVT-X03_20250523 | 5/23 | Add RJ45 Loopback Cable. (PM instructions) | None | None
Clemente-System_RMC L10 BOM-SE-PVT-X04_20250529 | 5/29 | Update 07- RMC LCCU internal Power cable (Cold & hot water) (Follow Quanta updates) | None | None
Clemente-System_RMC L10 BOM-SE-PVT-X05_20250603 | 6/03 | Update Cable 2nd Source (11 items) | None | None